## SCOPE (hidden)
ID | Scope Item | Flow Group | Tier | MoSCoW | Effort | Est_Days | Dev_Type | Pilot_6W | Week | Status | Notes
S01 | User login via Keycloak SSO | Infrastructure — Auth | Nice-to-have | Should | S | 1.5 | Integration | In | TBC | Confirmed | PKCE flow; NextAuth.js v5; no local passwords; role from Keycloak token
S02 | Role-based access control (sales / boost-ops / admin) | Infrastructure — Auth | Nice-to-have | Should | S | 1 | Non-AI | In | TBC | Confirmed | Middleware enforcement on every API route and page; bundled with S01
| **Very simple role defination |  | MVP | Must |  |  |  |  | TBC
S03 | Local user auto-provisioning on first login | Infrastructure — Auth | Nice-to-have | Should | S | 0.5 | Non-AI | In | TBC | Confirmed | User record created from Keycloak token on first login; bundled with S01
S04 | Messenger contact management by admin / ops | Infrastructure — Auth | MVP | Must | S | 1.5 | Non-AI | In | TBC | Confirmed | WhatsApp phone or Telegram chat ID per user; ops/admin can set
S05 | Ad account permission model | Infrastructure — Auth | MVP | Must | M | 3 | Non-AI | TBC | TBC | TBC-5 | Per-user whitelist vs client/brand mapping — decision changes implementation significantly
*Gloria choose
S06 | Emergency local user block | Infrastructure — Auth | Nice-to-have | Could | S | 1 | Non-AI | Out | TBC | Confirmed | Admin sets isActive=false as emergency override; defer to post-pilot
S26 | WhatsApp outbound messaging | Infrastructure — Messaging | MVP | Must | M | 3 | Integration | In | TBC | Confirmed | Sends: L1 question, L2 question, campaign live, rejected. Retry 3x on failure.
ver 1: link ver 2: full?
S27 | Telegram outbound messaging | Infrastructure — Messaging | Nice-to-have | Should | M | 2 | Integration | Out | TBC | Confirmed | Alternate channel switched by env var; same adapter interface; not needed for pilot
S28 | Two-way messaging channel | Infrastructure — Messaging | MVP | Must | M | 3 | Integration | TBC | TBC | TBC-1 | Whether channel is notification-only or interactive — see TBC-1. CS feedback (S53/S54) leans toward two-way.
| Whatsapp validation notification |  | MVP | Should
| System - initial suggestion about requests |  | MVP | Must
| System - CS enquiries about requests |  | Nice-to-have | Should
S53 | WhatsApp AI assistant — CS enquiries about requests | Infrastructure — Messaging | Nice-to-have | Should | M | 3 | AI | Out | TBC | New | CS WhatsApps questions about their own requests (status, rejection reason, what ops needs). AI reads request context and answers. Requires two-way channel (S28/TBC-1). Phase 2.
S54 | WhatsApp ad-hoc boost request via AI | Infrastructure — Messaging | Post-MVP | Could | L | 5 | AI | Out | TBC | New | CS describes a new campaign over WhatsApp; AI creates a draft request record. Ops reviews as normal. Complex intake flow outside portal — Post-MVP.
S29 | Ops alerts and badges > messaging | Infrastructure — Messaging | MVP | Must | S | 1 | Non-AI | In | TBC | Confirmed | Pending_approval badge, error alert, Loop 2 reply indicator — in-app only
S30 | Notification log retention | Infrastructure — Messaging | Nice-to-have | Should | S | 1 | Non-AI | Stretch | TBC | Confirmed | Append-only log per message; include if time allows after core items
S07 | New request intake form | CS — Create Request | MVP | Must | L | 5 | Non-AI | In | TBC | Confirmed | Form panels; CS fills business intent fields; auto-save draft; no AI chat in pilot — see S08
S08 | AI chat field extraction — chat panel (Workflow E) | CS — Create Request | MVP | Must | M | 3 | AI | Out | TBC | Confirmed | Defer to Phase 2. Chat panel beside form; CS describes campaign; AI fills Meta fields. Mutually exclusive with S51 — pick one UX.
S51 | AI field suggestion — Smart Fill inline (Workflow E) | CS — Create Request | MVP | Must | M | 3 | AI | Out | TBC | New | Alternative to S08 chat panel. AI suggestion embedded inside each form section; CS types plain language; AI auto-fills fields below. Same Workflow E backend, different UX. Pick S08 OR S51.
PP intake request / budget
S09 | Hard field validation at submission | CS — Create Request | MVP | Must | S | 0.5 | Non-AI | In | TBC | Confirmed | Different field sets: organic vs dark post; blocks submit if incomplete
S10 | Request submission flow (CS > AI ver > Gloria valid > approve) **define what CS need to edit **AI prefill form > AI validate | CS — Create Request | MVP | Must | S | 0.5 | Non-AI | In | TBC | Confirmed | draft → submitted; requestNum assigned; triggers validation
S11 | Request number auto-assignment ** follow autoboost | CS — Create Request | MVP | Must | S | 0.5 | Non-AI | In | TBC | TBC-6 | Format TBC but implementation is simple regardless of prefix
S48 | Real-time Meta reference data for form dropdowns **daily sync | CS — Create Request | MVP | Must | M | 1.5 | Integration | In | TBC | New | Fetch live enum values from Meta (via Pipeboard MCP or cached API): campaign objectives, buying types, performance goals (per objective), conversion locations. Populate form dropdowns; cache with short TTL. Prevents hardcoding values that Meta may change.
S50 | Similar past campaigns — template auto-fill | CS — Create Request | MVP | Should | M | 2 | AI | Out | TBC | New | During intake, surface top 3 past campaigns matching client + objective. CS clicks to auto-fill form fields from that template. Requires embedding/similarity search over historical requests.
S52 | AI targeting interest suggestion + | CS — Create Request | Nice-to-have | Should | M | 2 | AI | Out | TBC | New | AI suggests relevant Meta interest categories based on campaign brief. CS can copy a plain-language targeting summary to paste into client confirmation email. Builds on S08/S51 AI backend; adds formatted copy output.
| client-shareable draft |  | Nice-to-have | Could
S55 | Draft submission reminder — UI indicator | CS — Create Request | Nice-to-have | Should | S | 0.5 | Non-AI | In | TBC | New | Prominent in-portal indicator when CS has unsaved or unsubmitted drafts (banner or badge on request list). No automated notification — just clear UI state. Automated WhatsApp nudge deferred to Phase 2 (S55b).
S16 | CS field editing after submission | CS — Create Request | MVP | Should | M | 2 | Non-AI | Out | TBC | TBC-3 | Whether post-submit CS edits trigger re-validation — see TBC-3; defer
S18 | AI soft validation — 4 checks (Workflow A) | AI — Validate | MVP | Must | L | 5 | AI | Out | TBC | Confirmed | Defer to Phase 2 — ops reviews manually in pilot. Saves 5 days. Landing page, dates, objective, ad account.
S49 | AI request scoring — quality score + risk level | AI — Validate | Nice-to-have | Should | M | 3 | AI | Out | TBC | New | After validation, AI computes a 0–100 quality score and Low/Medium/High risk level per request. Displayed as SCORE and RISK columns on the request list. Single AI eval pass; both outputs stored on AgentRun. Depends on S18.
S19 | Validation result storage (AgentRun records) | AI — Validate | MVP | Must | S | 0.5 | AI | Out | TBC | Confirmed | Depends on S18; defer with it
S20 | Validation re-trigger after Loop 1 reply (*Under AI validation > Ready to review > review complete) | AI — Validate | MVP | Must | S | 0.5 | AI | Out | TBC | Confirmed | Depends on S18; defer with it
S21 | Loop 1 — AI sends clarification question to CS | AI — Loop 1 | MVP | Must | M | 2 | AI | Out | TBC | Confirmed | Depends on S18; defer to Phase 2
S22 | Loop 1 — CS reply capture and field update (Workflow B) | AI — Loop 1 | MVP | Must | M | 3 | AI | Out | TBC | TBC-2 | Depends on S18 and TBC-1/TBC-2; defer
S25 | Clarification Q&A history on request detail | AI — Loop 1 | Nice-to-have | Should | S | 1 | Non-AI | Out | TBC | Confirmed | No clarification loops in pilot; defer with S21-S22
S12 | Request list and queue | Ops — Review | Nice-to-have | Must | M | 3 | Non-AI | In | TBC | Confirmed | Filterable by status / date / requester; ops see all; CS see own; paginated
S58 | Request list — expandable adset drill-down *but must include adset data | Ops — Review | Nice-to-have | Should | M | 2 | Non-AI | Out | TBC | New | List rows show campaign-level summary; clicking expand reveals adset(s) inline without navigating away. Phase 2 enhancement to S12 — pilot uses full detail page (S13) for adset view.
S13 | Request detail page — view and edit | Ops — Review | MVP | Must | L | 5 | Non-AI | In | TBC | Confirmed | Campaign / Ad Sets / Ads sections; role-gated read-only and edit modes; largest UI item
S14 | CS field editing on draft (some status can edit) | Ops — Review | MVP | Must | M | 2 | Non-AI | In | TBC | Confirmed | CS edits business intent fields while status=draft; display on same detail page
S15 | Ops field editing before approval (Save Changes) > Long to decide | Ops — Review | MVP | Must | M | 3 | Non-AI | In | TBC | Confirmed | PATCH /api/requests/:id/fields; Meta config fields only; deep merge for targeting
S23 | Loop 2 — ops sends clarification question from dashboard ops system send > cs whatsapp receive | Ops — Loop 2 | MVP | Should | M | 2 | Non-AI | Out | TBC | Confirmed | Ops uses direct messaging in pilot; add in Phase 2
S24 | Loop 2 — CS reply capture and return to ops queue *Ops > CS > AI > Ops | Ops — Loop 2 | MVP | Should | M | 2 | Non-AI | Out | TBC | TBC-2 | Depends on TBC-2; defer
S33 | Loop 2 — ops clarification action button on review page | Ops — Loop 2 | MVP | Should | S | 1 | Non-AI | Out | TBC | TBC-4 | Defer — ops contacts CS directly in pilot; see TBC-4
S35 | Bridge mode auto-routing | Ops — Decision | MVP | Must | M | 2 | Non-AI | In | TBC | Confirmed | lib/bridge-routing.json; first-match-wins; Pipeboard as default in pilot
S36 | Bridge mode override by ops | Ops — Decision | Nice-to-have | Should | S | 1 | Non-AI | Stretch | TBC | Confirmed | Dropdown on review page; include if time allows
S31 | Ops approve action | Ops — Decision | MVP | Must | M | 3 | Non-AI | In | TBC | Confirmed | adAccountId validated; bridge mode confirmed; Workflow D triggered; → active
S32 | Ops reject action (with reason) Whatsapp CS > CS update > AI | Ops — Decision | Nice-to-have | Must | S | 1 | Non-AI | In | TBC | Confirmed | Reason stored; CS notified via WhatsApp; rejected status (re-submittable)
S17 | Request re-submission after rejection | Ops — Decision | Nice-to-have | Should | M | 2 | Non-AI | Stretch | TBC | Confirmed | CS views reason; chooses to re-submit; request reverts to draft; fits in W5-6
S34 | Ops send-back action (softer than reject) **minimal | Ops — Decision | Nice-to-have | Could | M | 2 | Non-AI | Out | TBC | TBC-4 | Post-pilot; TBC-4 decision needed
S37 | Campaign creation via Pipeboard MCP (Workflow D) | Campaign — Creation | MVP | Must | L | 5 | Integration | In | TBC | Confirmed | n8n Workflow D; creates campaign + adset + ad as ACTIVE; highest effort integration item
S38 | Campaign creation via Autoboost API (Workflow D) | Campaign — Creation | MVP | Must | L | 5 | Integration | Stretch | TBC | Confirmed | Editorial / BU platform / video dark posts; same Workflow D, autoboost path; add if time allows
S42 | Campaign live notification to CS | Campaign — Creation | Nice-to-have | Must | S | 0.5 | Non-AI | In | TBC | Confirmed | WhatsApp message sent when creating_campaign → active
S39 | Campaign creation error state and ops alert | Campaign — Errors | Nice-to-have | Must | M | 2 | Non-AI | In | TBC | Confirmed | Error state on Workflow D failure; ops alerted via dashboard
S40 | Error recovery path A — re-trigger system | Campaign — Errors | Nice-to-have | Must | S | 0.5 | Non-AI | In | TBC | Confirmed | Ops re-approves; Workflow D re-runs; error record retained for audit
S41 | Error recovery path B — ops enters Meta IDs manually | Campaign — Errors | Nice-to-have | Should | M | 2 | Non-AI | Out | TBC | Confirmed | Ops enters IDs after creating in Ads Manager; manuallyCreated=true flag; defer
S43 | Immutable audit event log (log file MVP, strutural NTH) | Audit | MVP | Must | M | 3 | Non-AI | Stretch | TBC | Confirmed | INSERT-only; every status change, approval, rejection, field update, campaign creation
S44 | Audit log query for admin | Audit | Nice-to-have | Should | S | 1 | Non-AI | Out | TBC | Confirmed | Filterable query endpoint; admin-only; defer to post-pilot
S56 | Meta estimated reach and cost estimate | Post-MVP | Post-MVP | Won't | M | 3 | Integration | Out | TBC | New | Display Meta's pre-campaign estimated reach and estimated cost per result based on targeting + budget. CS uses to confirm with client before submission. Requires Meta Reach & Frequency Estimation API. Phase 2.
S57 | Campaign health monitoring — unpublished / paused ad detection | Post-MVP | Post-MVP | Won't | M | 3 | Integration | Out | TBC | New | Periodic sync to detect when a live campaign's ad is not actually delivering (Meta rejected creative, account issue, ad paused). Alert ops/CS via dashboard or WhatsApp. Phase 2 — pilot relies on manual Ads Manager checks.
S45 | Campaign completed status detection | Post-MVP | Post-MVP | Won't | L | 5 | Non-AI | Out | TBC | Confirmed | Sync worker detects past end date; transitions active → completed
S46 | Campaign performance data (spend / impressions) | Post-MVP | Post-MVP | Won't | XL | 10 | Integration | Out | TBC | Confirmed | Meta Graph API performance sync; not captured in pilot
S47 | Reporting and analytics dashboard | Post-MVP | Post-MVP | Won't | XL | 10 | Non-AI | Out | TBC | Confirmed | Not in scope for pilot; ops uses request list

## MVP Scope (hidden)
ID | Scope Item | Flow Group | Effort | Est_Hours | Days | Dev_Type | Dev | Week | Column 10
S00 | Environment & CICD setup | Infrastructure — Base | S | 0 | 0 | Non-AI | Devops | Week 0
S01 | Internal Requirement and Spec alignment | Requirement | S | 16 | 2 | Non-AI | Denis, Leen (AI) | Week 0
S02 | Project setup & Database migration | Infrastructure — Base | S | 4 | 0.5 | Non-AI | Denis | Week 0
S03 | Freelancer Requirement and Spec alignment | Requirement | S | 16 | 2 | Non-AI | Melvin | Week 1
S04 | Feasibility Study - Chat mode suggestion and update DB and feedback | Feasibility Study | L | 40 | 5 | AI | Leen (AI) | Week 1
S05 | Simple AutheN with role - CS, Boosting, Admin | Infrastructure — Auth | S | 4 | 0.5 | Non-AI | Denis | Week 2
S06 | Role based access control | Infrastructure — Auth | M | 16 | 2 | Non-AI | Denis | Week 6
S07 | User x TG mapping | Infrastructure — User | S | 4 | 0.5 | Non-AI | Melvin | Week 3
S08 | Request Listing page - Campaign level | Request Listing | S | 8 | 1 | Non-AI | Denis | Week 2
S09 | Request Listing page - Adset info | Request Listing | S | 4 | 0.5 | Non-AI | Denis | Week 6
S10 | Request Form - Init from PP system (with BA no.) | Request Form | S | 8 | 1 | Non-AI | Denis | Week 1
S11 | Request Form - CS form view | Request Form | S | 12 | 1.5 | Non-AI | Melvin | Week 1
S12 | Request Form - Chat Interface (no AI integration) | Request Form | S | 8 | 1 | Non-AI | Melvin | Week 2
S13 | Request Form - Chat Experience (n8n setup) | Request Form | S | 6 | 0.75 | Non-AI | Melvin | Week 2
S14 | Request Form - Chat Experience (AI request suggestion) | Request Form | M | 24 | 3 | AI | Leen (AI) | Week 2
S15 | Request Form - Chat Interface (n8n AI integration) | Request Form | S | 8 | 1 | Integration | Melvin | Week 2
S16 | Request Form - AI suggestion autofill | Request Form | S | 8 | 1 | Integration | Melvin | Week 2
S17 | Request Form - Daily Sync field option from Meta | Request Form | S | 16 | 2 | Integration | Denis | Week 1
S18 | Request Form - Save form before submit | Request Form | S | 2 | 0.25 | Non-AI | Denis | Week 2
S19 | Request Form - Hard field validation | Request Form | S | 2 | 0.25 | Non-AI | Denis | Week 2
S20 | Request Form - Form submission | Request Form | S | 2 | 0.25 | Non-AI | Denis | Week 3
S21 | Request Validation - AI validation n8n setup | Request Validation | S | 4 | 0.5 | Non-AI | Melvin | Week 3
S22 | Request Validation - Trigger AI validation after form submit | Request Validation | S | 4 | 0.5 | Integration | Melvin | Week 3
S23 | Request Validation - AI request validation 1. validate success - pass 2. validate fail - no need CS and self healing 3. validate fail - need CS interaction | Request Validation | M | 24 | 3 | AI | Leen (AI) | Week 3
S24 | Request Validation - TG connection | Request Validation | S | 4 | 0.5 | Integration | Melvin | Week 3
S25 | Request Validation - Send validation problem to CS via TG with link | Request Validation | S | 4 | 0.5 | Non-AI | Melvin | Week 3
S26 | Request Validation - CS reply and validation loop (need to handle chat context) | Request Validation | M | 16 | 2 | Integration | Melvin | Week 3
S27 | Request Validation - Validation success | Request Validation | S | 2 | 0.25 | Non-AI | Melvin | Week 4
S28 | Request Review - Boosting review listing | Request Review | S | 2 | 0.25 | Non-AI | Denis | Week 3
S29 | Request Review - Boosting review form view | Request Review | S | 2 | 0.25 | Non-AI | Denis | Week 3
S30 | Request Review - Choose Ad account from list | Request Review | S | 8 | 1 | Non-AI | Denis | Week 3
S31 | Request Review - Boosting feedback function | Request Review | S | 8 | 1 | Non-AI | Melvin | Week 4
S32 | Request Review - Send Boosting feedback to CS via TG with link | Request Review | S | 4 | 0.5 | Integration | Melvin | Week 4
S33 | Request Review - Boosting update without feedback | Request Review | S | 4 | 0.5 | Non-AI | Melvin | Week 4
S34 | Request Review - CS update and resubmit | Request Review | S | 4 | 0.5 | Non-AI | Melvin | Week 4
S35 | Request Review - Approve Request | Request Review | S | 2 | 0.25 | Non-AI | Melvin | Week 4
S36 | Meta Creation - Creation method routing & mapping | Meta Creation | S | 4 | 0.5 | Non-AI | Melvin | Week 5
S37 | Meta Creation - Autoboost Integration | Meta Creation | M | 24 | 3 | Non-AI | Denis | Week 4
S38 | Meta Creation - Autoboost Result | Meta Creation | S | 4 | 0.5 | Non-AI | Denis | Week 5
S39 | Meta Creation - Autoboost Case Testing | Meta Creation | S | 16 | 2 | Non-AI | Denis | Week 5
S40 | Meta Creation - MCP integration (n8n setup) | Meta Creation | S | 8 | 1 | Non-AI | Melvin | Week 5
S41 | Meta Creation - MCP integration (response & integrate MCP) | Meta Creation | S | 8 | 1 | Integration | Melvin | Week 5
S42 | Meta Creation - MCP integration (result to system) | Meta Creation | S | 4 | 0.5 | Integration | Melvin | Week 5
S43 | Meta Creation - Campaign live notification to CS | Meta Creation | S | 2 | 0.25 | Integration | Denis | Week 5
S44 | Debuging & Bugfixing | Bugfixing | M | 24 | 3 | Non-AI | Melvin | Week 6

## Meta Form
Module | Field | Fill By | Field Type | Field Nature | Default Value | Logic | Sample Value | Remarks | Data Source | Clarification required
Request | Project ID | Static | Text | None
Request | BA Number | System | Text | None
Request | Client | System | Text | None
Request | Client ID | Static | Number | None
Request | Sales | System | Text | None
Request | Sales Email | Static | Text | None
Request | Budget | System | Number | None
Campaign | Ad Account | Boosting | Single Select | Sync | — |  | act_123456 | [POST] /act_<AD_ACCOUNT_ID>/campaigns — Ops selects from permitted ad accounts before approval — required before Workflow D runs not found in ads manager | /me/adaccounts?fields=id,name,account_id,account_status,amount_spent,balance,currency,age,business_city,business_country_code,business{owned_pages{id,username,name,instagram_business_account{id,username}}} | Mapping? or fill?
Campaign | Campaign Status | Static | Single Select | Static | PAUSED |  | PAUSED | payload.status - Always PAUSED on creation — Ops activates manually via dashboard Activate action (no Meta API call at activation) not found in ads manager
Campaign | Special Ad Categories | Static | Multi Select | Static | None |  | None (empty) | Required Meta API field on every campaign — set to empty [] for standard non-restricted campaigns — must be declared explicitly
Campaign | Choose a buying type | CS | Single Select | Static | Auction |  | Auction | payload.buying_type → AUCTION ¦ RESERVED |  | CS or Boosting fill?
Campaign | Choose a campaign objective | CS | Single Select | Static | Awareness |  | Awareness | payload.objective: OUTCOME_APP_PROMOTION (AUCTION only) OUTCOME_AWARENESS OUTCOME_ENGAGEMENT OUTCOME_LEADS (AUCTION only) OUTCOME_SALES (AUCTION only) OUTCOME_TRAFFIC (AUCTION only)
Campaign | Advantage+ campaign budget | Static | Toggle | Static | OFF |  | OFF
Campaign | A/B test | Static | Toggle | Static | OFF |  | OFF
Campaign | Campaign name | System | Text | None | — |  | BANum _Client Name_Objective_Page Name_Boost Objective | payload.name → Campaign name
Campaign | Campaign objective | CS | Single Select | Static | — |  | Awareness | payload.objective — same source as above (confirms the selected objective) duplicated
Campaign | Use adset level budgets | Boosting, CS | Toggle | Static | ON |  | ON | Always ON — campaign itself has no budget — ⚠️ corrected Field Type from Date to Toggle Not found in ads manager |  | CS or Boosting fill?
Campaign | Add campaign spending limit |  | Toggle
Campaign | Share some of your budget with other ad sets |  | Toggle
Ad sets | Ad set name | System | Text | None | — |  | BANum _Client Name_Objective_Page Name_Boost Objective | payload.name → {audienceLabel}_{requestNum} _{clientName}_{objective}_{pageName}_Boost Objective — audienceLabel = Interest_ ¦ Website_ ¦ Lookalike_ ¦ Engagement_
Ad sets | Conversion Location | CS | Single Select | Static | — |  | Website | derived from objective: Traffic → Website ¦ Engagement → ON_AD ¦ Awareness → omitted Not pass data to api Not found in ads manager | https://developers.facebook.com/documentation/ads-commerce/marketing-api/reference/ad-campaign#restrictions | System or Boosting fill?
Ad sets | Performance goal | CS | Single Select | Static | — |  | Maximize number of link clicks | payload.optimization_goal — must be valid combo with objective (see model-02-request.md#objective-performance-goal)
Ad sets | Frequency Control | Boosting | Object | None | — |  | 3 times every 7 days | payload.frequency_control_specs: [ {"event": "IMPRESSIONS", "interval_days": 7, "max_frequency": 3} ] An array of frequency control specs for this ad set. Writes to this field are only available in ad sets where REACH and THRUPLAY are the performance goal. Event name, only IMPRESSIONS currently.
Ad sets | Budget | CS | Single Select | Static | Lifetime budget |  | Lifetime budget ¦ Daily budget
Ad sets | Lifetime budget | CS | Number | None | — |  | 200 | payload.lifetime_budget (**Budget in cents.** HK$300 = 30000 cents. Always convert before passing.)
Ad sets | Daily budget | CS | Number | None | — |  | 200 | payload.daily_budget (**Budget in cents.** HK$300 = 30000 cents. Always convert before passing.)
Ad sets | Reach your preferred audiences | Static | Single Select | Static | Further limit the reach of your ads |  | Further limit the reach of your ads | Always manual audience mode — Advantage+ Audience = OFF
Ad sets | Advantage+ campaign budget | Static | Toggle | Static | OFF |  | OFF | Always OFF — hardcoded
Ad sets | Platform?? | Static | Single Select | Static | Facebook |  | Facebook | Ad account / page name — static for this deployment Not found in ads manager |  | System or Boosting? How to set?
Ad sets | Start Date | CS | DateTime | None | — |  | 2026-05-22 10:00 (HKT) | payload.start_time
Ad sets | End Date | CS | DateTime | None | — |  | 2026-05-23 23:59 (HKT) | payload.end_time
Ad sets | Buying type | Boosting, TBC | Single Select | Static | Auction |  | Auction | Always AUCTION — repeated at ad set level Not found in ads manager |  | Boosting? How to set?
Ad sets | Budget / Advantage+ campaign budget | Static | Toggle | Static | OFF |  | OFF | Always OFF unconditionally Duplicated?
Ad sets | Share some of your budget with other ad sets | Static | Toggle | Static | OFF |  | OFF | Always OFF — payload.shareBudgetWithOtherAdSets Not found in ads manager Ad sets
Ad sets | A/B test | Static | Toggle | Static | OFF |  | OFF | Always OFF — payload.abTest
Ad sets | Facebook Page | CS, Boosting | Single Select | Sync | — |  | CapTV 擷電視 | payload.promoted_object: {"page_id":FACEBOOK_PAGE_ID}
Ad sets | Cost per result goal | —, Static | Number | None | — (blank) |  | XXXX | Not set per spec — left blank in Workflow D Left blank (our case): Meta uses the Lowest Cost strategy — it spends the full budget and maximises results without any cost constraint. This is the standard approach for boosting.
Ad sets | Switch to original audience options | Boosting, CS | Action | Static | — |  | Switch to original audience options | Always use manual/original audience mode (not Advantage+ Audience)
Ad sets | Custom audiences | CS | Multi Select | Real Time | — |  | everyone who engaged with CapTV, Lookalike (10%) - everyone who engaged with CapTV | payload.targeting.custom_audiences: [{"id": "23850000000000"}] | /act_<AD_ACCOUNT_ID>/customaudiences?fields=id,name,description,audience_size,time_created,approximate_count_lower_bound,approximate_count_upper_bound,operation_status&limit=100
Ad sets | Advantage+ custom audience | Static | Toggle | None | OFF |  | OFF | payload.targeting_relaxation_types: { "custom_audience": 0 } Meta will auto-added {"lookalike":1, "custom_audience":1} if not set | 0 (OFF) ¦ 1 (ON)
Ad sets | Locations | CS | Multi Select | Sync | HK |  | HK | payload.targeting.geo_locations: [{"countries": ["HK"]}] | /search?type=adgeolocation&fields=name,key&limit=1000
Ad sets | Age | CS | Range | None | 25-55 |  | 25-55 | payload.targeting.[age_min / age_max] — defaults 25 / 55 — use 65 for 65+ Deprecated, only min age now
Ad sets | Gender | CS | Single Select | Static | All |  | All | payload.targeting.genders: [0] Not found in ads manager | 0 (All) ¦ 1 (Male) ¦ 2 (Female)
Ad sets | Include people who match | CS | Multi Select | Real Time | — |  | Demographics : Newly engaged (1 year), Newly engaged (3 months), Newly engaged (6 months), Newlywed (1 year), Newlywed (3 months), Newlywed (6 months) | payload.targeting.flexible_spec: [ { "interests": [{"id": "6003139266461", "name": "Shopping"}], "behaviors": [{"id": "123456", "name": "Frequent travelers"}] } ] Deprecated, new feild is "Exclude these custom audiences" | /act_<AD_ACCOUNT_ID>/targetingsearch?q={KEYWORD}&limit=100&limit_type=interests limit_type: interests,education_schools,education_majors,work_positions,work_employers,relationship_statuses,college_years,education_statuses,family_statuses,industries,life_events,behaviors,income
Ad sets | Languages | CS | Multi Select | Sync | English (all), Chinese (all) |  | English (all), Chinese (All) | payload.targeting.locales: [1004, 1001] | /search?type=adlocale&fields=name,key&limit=200
Ad sets | Placements | CS | Multi Select | Static | Facebook Feed |  | Facebook Feed, Facebook Stories, Instagram Feed, Instagram Stories | payload.targeting: { "publisher_platforms": ["facebook", "instagram"], "facebook_positions": ["feed", "story"], "instagram_positions": ["stream", "story"], } | https://developers.facebook.com/documentation/ads-commerce/marketing-api/audiences/reference/placement-targeting#newplacement
Ad sets | Exclude these custom audiences |  | Multi Select | Real Time
Ad sets | Devices |  | Single Select
Ad sets | Value rules |  | Object |  |  |  |  | to be further expanded if needed
Ad sets | Delivery type |  | Single Select
Ad sets | Dynamic creative |  | Toggle
Ad sets | Budget scheduling |  | Object |  |  |  |  | to be further expanded if needed
Ad sets | Specific mobile devices & operating systems |  | Single Select
Ad sets | Only when connected to WiFi |  | Toggle
Ad sets | Exclude skippable ads |  | Toggle
Ad sets | In-content ads |  | Single Select
Ad sets | Audience Network ads |  | Single Select
Ad sets | Who can comment on your ads |  | Single Select
Ad sets | Publisher block lists
Ad sets | Exclude live videos |  | Toggle
Ad sets | Exclude nonpartner-publishers |  | Toggle
Ads | Ad setup | CS | Single Select | Static | Use existing post |  | Use existing post | organic → Use existing post dark → Create ad
Ads | Ad creative [organic post] | CS | Text | None | — |  | facebook post id / post link: 228538523933411_1883467985713686 https://facebook.com/228538523933411_1925600341500450 instagram post link (MCP will convert to media_id): https://www.instagram.com/p/DYUnnPCEiuA/ | [Creative] (Have to create the creative before creating ad) {facebookPageId}_{postId} extracted from payload.postUrl
Ads | Ad creative [dark post] | CS | File | None | — |  | [image / video files] OR [image / video links] | [Creative] (Have to create the creative before creating ad) payload.creativeAsset — dark posts only (image file) — video dark posts are auto-routed to autoboost and do not reach this flow
Ads | Caption [dark post] | CS | Text | None | — |  | [ad body text] | payload.caption — ad body copy for dark posts only Primary text in ads manager
Ads | Headline [dark post] | CS | Text | None | — |  | [headline text] | payload.headline — optional ad headline for dark posts only
Ads | Call to Action | CS | Single Select | Static | NO_BUTTON |  | LEARN_MORE | [Creative] payload.call_to_action: { "type": "NO_BUTTON ¦ LEARN_MORE ¦ SHOP_NOW ¦ SIGN_UP ¦ NO_BUTTON" }
Ads | Website URL | CS | URL | None | — |  | https://www.weekendhk.com/ | [Creative] payload.call_to_action: { "value": {"link_url": URL} }
Ads | Multi-advertiser ads | Static, TBC | Toggle | Static | OFF |  | 0 (OFF) ¦ 1 (ON) | payload.multi_advertiser_ads: 0 |  | Always OFF?
Ads | Placements | CS, TBC | Multi Select | Static | Facebook Feed |  | Facebook Feed | Same as ad set payload.placements — default FACEBOOK_FEED
Ads | Identity - Facebook Page | Static | Label | Sync | CapTV 擷電視 |  | CapTV 擷電視 | [Creative] payload.page_id: FACEBOOK_PAGE_ID IG Post payload.object_id: FACEBOOK_PAGE_ID | /me/adaccounts
Ads | Identity - Instagram profile | CS, System, TBC | Single Select | Sync | captv.hk |  | captv.hk | payload.instagram_user_id: IG_USER_ID | /me/adaccounts
Ads | Multi-advertiser ads | Static | Toggle | Static | OFF |  | OFF | Always OFF
Ads | Catalogue | Boosting, TBC | Single Select | Sync | — (null) |  | Catalogue | payload.catalogue — null for standard ads — Ops-set for catalogue / dynamic campaigns only Not found in ads manager |  | How to set?
Ads | Source URL | Static | URL | None | OFF |  | OFF | payload.landingPageUrl — required for Traffic objective and dark posts — OFF for organic Not found in ads manager
Ads | Site links | Static | Multi Text | None | OFF |  | OFF | payload.siteLinks — Traffic objective only — OFF otherwise Not found in ads manager
Ads | Advantage+ creative text generation | Static | Toggle | Static | OFF |  | OFF | payload.advantageCreativeTestGeneration — always OFF
Ads | Advantage+ creative enhancements | Static | Multi Select | Static | OFF |  | OFF | [Creative] payload.degrees_of_freedom_spec: { "creative_features_spec": { "standard_enhancements": { "enroll_status": "OPT_OUT" }, ... } } enroll_status: OPT_OUT(OFF) ¦ OPT_IN (ON) | https://developers.facebook.com/docs/marketing-api/reference/ad-creative-features-spec
Ads | Essential enhancements | Static | Toggle | Static | OFF |  | OFF | [Creative] payload.degrees_of_freedom_spec: ... Not found in ads manager
Ads | Tracking | Boosting | Single Select | Static | Website events |  | Website events | payload.tracking_specs: [{ "action.type": ["offsite_conversion"], "fb_pixel": ["<PIXEL_ID>"] }] It appears as a section instead of a field
Ads | Pixel ID | Boosting | Single Select | Sync | — |  | 1624562068593082 | payload.tracking_specs: [{ "action.type": ["offsite_conversion"], "fb_pixel": ["<PIXEL_ID>"] }] |  | can default set?
Ads | Post ID |  | Text |  |  |  |  | post ID for selecting dark post
Ads | Ad name |  | Text
Ads | Partnership ad |  | Toggle
Ads | Threads profile |  | Single Select |  |  |  | Use Instagram account
Ads | Ad setup format |  | Single Select |  |  |  | Create ad
Ads | Destination |  | Single Select |  |  |  | Website
Ads | See more display link |  | URL
Ads | Mobile app |  | Single Select
Ads | Browser add-ons |  | Single Select |  |  |  | None
Ads | Flexible media |  | Toggle
Ads | Add music |  | Toggle
Ads | Music type |  | Single Select |  |  |  | Automatically apply music
Ads | Music |  | Single Select
Ads | Add a destination |  | Toggle
Ads | Description |  | Text |  |  |  | [description text] | description options for dark post
Ads | Create testing |  | Object |  |  |  |  | to be further expanded if needed
Ads | Website events |  | Toggle
Ads | Offline events |  | Toggle
Ads | Dataset ID |  | Single Select |  |  |  |  | Dataset ID for Offline events
Ads | URL parameters |  | Text
Ads | View tags |  | Text
Ads | Third-party reporting tools |  | Object |  |  |  |  | to be further expanded if needed

## Field List
Field Name | Field Option | How to Sync
Ad Account | NF
Campaign Status | NF
Special Ad Categories | Financial products and services
Employment
Housing
Social issues, elections or politics
Choose a buying type | Auction
Reservation
Choose a campaign objective | Awareness
Traffic
Engagement
Leads
App promotion
Sales
Advantage+ campaign budget | (toggle)
A/B test | (toggle)
Campaign name | (text field)
Campaign objective | (duplicated)
Use adset level budgets | NF
Add campaign spending limit | (toggle)
Share some of your budget with other ad sets | (toggle)
Ad set name | (text field)
Conversion Location | NF
Performance goal | Maximize reach of goals
Maximize number of impressions
Maximize ad recall lift
Maximize ThruPlay views
Maximize 2-second continous video plays
Frequency Control
- Type | Cap / Target
- times | (number)
- days | (number)
Budget | Daily budget
Lifetime budget
Lifetime budget | (number)
Daily budget | (number)
Reach your preferred audiences | Stay in current setup
(actions) | Apply value rules with Advantage+ on
Further limit the reach of your ads
Advantage+ campaign budget | (toggle)
Platform?? | NF
Start Date | (date)
End Date | (date)
Buying type | NF
Budget / Advantage+ campaign budget | (duplicated)
Share some of your budget with other ad sets | NF
A/B test | (toggle)
Facebook Page | (picklist)
Cost per result goal | (number)
Switch to original audience options | (action)
Custom audiences | (picklist)
Advantage+ custom audience | (toggle)
Locations | (picklist)
Age (min) | [18 - 25]
Gender | NF
Include people who match | (deprecated)
Languages | (picklist)
Placements
Facebook Feed
Facebook profile feed
Facebook Marketplace
Facebook right column
Facebook Business Explore
Facebook Notifications
Facebook Stories
Facebook Reels
Facebook in-stream reels
Ads on Facebook Reels
Facebook search results
Instagram feed
Instagram profile feed
Instagram Explore home
Instagram Stories
Instagram Reels
Instagram search results
Threads feed
Messenger Stories
WhatsApp Status
Send a marketing message to people on WhatsApp when they are most likely to engage
Marketing messages on WhatsApp
Audience Network native, banner and interstitial
Audience Network rewarded videos
Devices | All devices
Mobile
Desktop
Exclude these custom audiences | (picklist)
Value rules | TBC
Delivery type | Standard
Pacing
Accelerated
Dynamic creative | (toggle)
Budget scheduling | TBC
Specific mobile devices & operating systems | All mobile devices
Android devices only
iOS devices only
Feature phones only
Only when connected to WiFi | (toggle)
Exclude skippable ads | (toggle)
In-content ads | Expanded inventory (default)
Moderate inventory
Limited inventroy
Audience Network ads | Expanded inventory (default)
Moderate inventory
Limited inventroy
Who can comment on your ads | Public (default)
No one
Publisher block lists | TBC
Exclude live videos | (toggle)
Exclude nonpartner-publishers | (toggle)
Ad setup | Create ad
Use existing post
Use Creative Hub mockup
Ad creative [organic post] | (text field)
Ad creative [dark post] | (file)
Caption [dark post] | (text field)
Headline [dark post] | (text field)
Call to Action | No button
Contact us
Download
Get directions
Get quote
Get showtimes
See details
Learn more
Listen now
Send message
Order now
Request time
Save
See menu
Shop now
Sign up
Subscribe
Watch more
Send Whatsapp message
Apply now
Book now
Website URL | (url)
Multi-advertiser ads | (toggle)
Placements | NF
Identity - Facebook Page | (label)
Identity - Instagram profile | (picklist)
Multi-advertiser ads | (toggle) (duplicated)
Catalogue | NF
Source URL | NF
Site links | NF
Advantage+ creative text generation | (toggle)
Advantage+ creative enhancements | TBC
Essential enhancements | NF
Tracking | NA
Pixel ID | (picklist)
Ad name | (text field)
Post ID | (text field)
Partnership ad | (toggle)
Threads profile | (picklist)
Ad setup format | Single image or video
carousel
Destination | instant experience
website
call
messaging apps
See more display link | url
Mobile app | (picklist)
Browser add-ons | None
messager
WhatsApp
Flexible media | (toggle)
Add music | (toggle)
Music type | Automatically apply music
Manually select music
Music | (picklist)
Add a destination | (toggle)
Description | (text field)
Create testing | TBC
Third-party reporting tools | TBC
Website events | (toggle)
Offline events | (toggle)
URL parameters | (text field)
View tags | (text field)
Dataset ID | (picklist)

## Meta Ads Manager Screens
Campaign
Ad sets
Ads

## From CS
78369-1065953-993669
FB： ﻿Facebookfacebook.com WeekendWeekly/posts/1388164203353879
IG： ﻿Instagraminstagram.com reel/DYE6c0pk3Jy/?igsh=bzJ4djNveGdhZW9s
Objective: Video Views 50% ＋ Post Engagement 50%
Period: 7 days
Budget： $10,000 (budget optimization between fb and ig feed)
Location: HK
Age: 21-59
Gender: All
Language: Chinese (All) , English (All)
Interests:
Family,Home, Wellcome, Supermarket, 惠康超級市場 Wellcome Supermarket, Department store, Cooking, Recipes (food & drink), Friends,Food & Wine, Food and Beverage,Frozen food, vegetables, Fruit ,Local food,Potato chip, Quality Foods, Snack food, Stay at Home ,city'super,Hong Kong Television Network, ParknShop,AmazonFresh, online grocery, Working Moms, Working Mother, Fresh Produce, Eggs, Frozen Food, Beef, Chicken, Fruit, Ham, Kitchenware, Tomato, Vegetable, Vegetable oil, Yogurt, Juice,ParknShop, Market Place by Jasons, Alcohol, Alcoholic beverages, Beer, wine,sake , Bakery, Beverages, Biscuit, Candy, sushi,Coupons, Groupon, Sales promotion, JetsoClub, 新假期JetSo, GetJetso.com, GetJetso.hk 香港著數優惠網, Discounting
Boosting Landing：https://www.instagram.com/hkwellcome/